## Sheet1
Category | Task | Status | Week
Player Movement & Camera | Implement WASD movement + Jump | Not Started | Week 1
Player Movement & Camera | Set up Mouse Look | Not Started | Week 1
Spell System | Create Fireball Prefab | Not Started | Week 1
Spell System | Implement fireball movement & physics | Not Started | Week 1
Spell System | Add basic explosion on impact | Not Started | Week 1
Basic Enemy System | Create an Enemy (Capsule/Placeholder) | Not Started | Week 1
Basic Enemy System | Implement NavMesh AI (Follow Player) | Not Started | Week 1
Basic Enemy System | Create Basic Damage System | Not Started | Week 1
Game Scene Setup | Create simple testing arena | Not Started | Week 1
Spell Enhancements | Add Explosion Radius & Knockback | Not Started | Week 2
Spell Enhancements | Implement Mana System | Not Started | Week 2
Enemy AI Improvements | Add Health System for Enemies | Not Started | Week 2
Enemy AI Improvements | Implement Death Animation | Not Started | Week 2
Enemy AI Improvements | Improve AI chase & attack behavior | Not Started | Week 2
UI Elements | Add Mana Bar & Health Bar | Not Started | Week 2
UI Elements | Display Enemy Health on Hit | Not Started | Week 2
Basic Sound Effects | Add Fireball Sound Effect | Not Started | Week 2
Basic Sound Effects | Add Enemy Hurt & Death Sounds | Not Started | Week 2
New Enemy Types | Troll: Slow, strong, high HP | Not Started | Week 3
New Enemy Types | Goblin: Fast, weak, melee | Not Started | Week 3
New Enemy Types | Skeleton: Ranged, poison attack | Not Started | Week 3
Spell Upgrades | Fireball Upgrade: Bigger explosion | Not Started | Week 3
Spell Upgrades | Unlock Lightning Spell | Not Started | Week 3
Tower Defense Mechanics | Create Tower Health System | Not Started | Week 3
Tower Defense Mechanics | Implement Enemy Attack on Tower | Not Started | Week 3
Scoring System | Add Kill Score Counter | Not Started | Week 3
Scoring System | Introduce Wave System | Not Started | Week 3
Polish Visuals & Effects | Add Fireball Explosion FX | Not Started | Week 4
Polish Visuals & Effects | Improve Enemy Hit Reaction Animations | Not Started | Week 4
Polish Visuals & Effects | Create Better Environment | Not Started | Week 4
User Interface & Menus | Create Start Menu & Game Over Screen | Not Started | Week 4
User Interface & Menus | Add Difficulty Selection | Not Started | Week 4
Balancing & Testing | Adjust Enemy HP & Speed | Not Started | Week 4
Balancing & Testing | Fine-tune Mana Regen & Spell Damage | Not Started | Week 4
Balancing & Testing | Playtest & Fix Bugs | Not Started | Week 4